Software Life cycle Overview
Software Life cycle Overview
By Masoud Kalali
March/2005
[Speaker Notes: This presentation made because At first : I see a need in RUP community for such presentation . Use of this presentation and all material included in it is free in respect the author which I used some of their word in my presentation. But pleas add my reference page at end of your presentation and a new entry for my own presentation.]

---
Presentation Goal
Presentation Goal
Have a better understanding of RUP
A brief in common Software development models
and a look at life cycle model in RUP in more
detail.
[Speaker Notes: What we will learn from this presentation ? An overview of RUP as a process Some details about RUP process and then we will take a very short look at RUP product from IBM After looking into it we will see how RUP and MSF will compare .]

---
Presentation Agenda
Presentation Agenda
Part I
  - Basics and Explanations
    - Terms and definitions
    - Well known Life Cycle models
        - Waterfall
        - Spiral
        - Iterative
        - XP
Part II
  - RUP as a SDP Life Cycle Model
    - Phases and Milestones
    - RUP and System Evolution
  - EUP (Explanation)

---
Part I
Part I
Terms and definitions
Software Development models

---
Terms and Explanations
Terms and Explanations
Life Cycle
    - A complete Pass through the phases.
    - Time from beginning the software developing to end of releasing.
    - Whole time which software or related documents in under work in development Organization
Phase
    - Time between two major project milestone.
    - Time which you decide to move the project to new State in its Life Cycle.

---
Terms and Explanations
Iteration
    - distinct sequence of activities.
    - Have base-lined plan and valuation criteria.
    - Resulting in a release.
Milestone
    - An end point for an iteration
    - Corresponds to release point
Artifacts (Deliverable):
    - Stakeholders use Artifacts to do activities
    - Stakeholders do activities to produce artifacts
    - Artifacts are responsibility of a role – worker (s)

---
Software Development Models
Software Development Models
Waterfall model *
Spiral model *
Iterative model *
XP model *
Prototyping model
Component assembly model
Concurrent development model
Formal methods model
* Will be reviewed briefly Today

---
Waterfall Development Characteristics
Delays confirmation of critical risk resolution
Measures progress by assessing work-products that are poor predictors of time-to-completion
Precludes early deployment
Frequently results in major unplanned iterations
Waterfall Process
Code and unit test
Design
Subsystem integration
System test
        Requirements
    analysis

---
Waterfall pros and cons
Waterfall pros and cons
Pros
    - Results in thoroughly debugged, robust stable system
Cons
    - Has no guideline for applying changes which occur during software development
    - The process is very rigid.
    - Late discovery of problems or changes to requirements leads to a costly roll back through the steps already completed
    - Produces large amounts of documentation, which should be unnecessary in a lightweight smart space project
    - Delays and aggregates integration and testing

---
Spiral Development Characteristics
Spiral Development Characteristics
Customer communication: Establish effective communication
Planning: Define resources, timelines etc.
Risk analysis: Assess technical and management risks
Construction & release: construct, test, install, provide user support
Customer evaluation: obtain feedback
Couples iterative nature of prototyping with controlled and systematic aspect of the linear sequential model
Early iterations may be paper models or prototypes
Can be used throughout the life of the product
Reduces risk if properly applied
Customer
Evaluation
Construction
& Release
Engineering
Risk
Analysis
Planning
Customer
Communication

---
Spiral Pros and Cons
Spiral Pros and Cons
Pros
    - Very thorough
    - Eventually leads to stable code
Cons
    - With every iteration, the cost and time increase
    - Leads to large volumes of documentation
    - Resulting systems are meant to be persistent and upgradeable, which is not a key factor in smart spaces

---
Iterative (Incremental) Development Characteristics
Iterative (Incremental) Development Characteristics
Resolves major risks before making large investments
Enables early user feedback
Makes testing and integration continuous
Focuses project short-term objective milestones
Makes possible deployment of partial implementations
Iteration 1
Iteration 2
Iteration 3
T I M E
I
C
D
R
T
I
C
D
R
T
I
C
D
R
T
[Speaker Notes: Iterative processes were developed in response to these waterfall characteristics. With an iterative process, the waterfall steps are applied iteratively. Instead of developing the whole system in lock step, an increment (that is, a subset of system functionality) is selected and developed, then another increment, etc. The selection of the first increment to be developed is based on risk, the highest priority risks first. To address the selected risk(s), choose a subset of use cases. Develop the minimal set of use cases that will allow objective verification (i.e., through a set of executable tests) of the risks that you have chosen. Then select the next increment to address the next highest risk, and so on. Thus you apply the waterfall within each iteration and the system evolves incrementally. In the iterative approach, the waterfall is applied to a single system increment at a time. Each iteration produces an executable.]

---
Iterative development
Iterative development
Pros
    - Risks are mitigated earlier.
      - Integration risks
      - Architectural risks
    - Change is more manageable.
    - There is a higher level of reuse.
    - The project team can learn along the way.
    - The product has better overall quality.
Cons
    - Existing software management project thinking and liking is with the waterfall model of development .
    - Continual changes tends to corrupt system structures, so long term software maintenance is difficult.
    - Need tighter management

---
XP development model
XP development model
Some XP Practices
Tests
Refactoring
Pair programming
Small releases
Simple design
Continuous integration
40-hour week
XP Principles
  - Rapid feedback
  - Assume simplicity
  - Incremental change
  - Embrace Change
  - Quality Work
The XP Cycle (In brief )
analysis
test
code
design

---
XP Development model
XP Development model
Pros
    - Very fast
    - Low cost
    - Results in lightweight, disposable solutions
    - No need for masses of documentation since the two programmers are in constant verbal communication anyway
Cons
    - Not suitable for developing large Scale systems.
    - Potential for bugs down the line if the initial test has not been properly designed

---
RUP The process in one page
RUP The process in one page
Our Today focus
Core Workflows
Supporting Workflows
Project Management
Environment
Business Modeling
Implementation
Test & Assessment
Analysis & Design
Deployment
Configure. & Change Mgmt
Requirements
Preliminary
Iteration(s)
 Iter.
#1
Phases
Iterations
 Iter.
#2
 Iter.
#n
 Iter.
#n+1
 Iter.
#n+2
 Iter.
#m
 Iter.
#m+1
Elaboration
Transition
Inception
Construction
Time : Dynamic Aspect
Stat
ic Aspect
[Speaker Notes: The picture shows how RUP static and dynamic aspect come together to form the most well known Software development process. As you can see each workflows affect some of Iterations stronger and does not have any effect or a very small effect on others , its because of the nature of each workflow ,Any work flow as defined have its own containment and goal. for example : Business modeling happen mostly during inception and elaboration phase because we should determine almost all Business models up to the end of Elaboration (80 percent of models should be ready). Or implementation works are done mostly in construction phase and some of it is left for transition (for example developing some tools for data migration…) and some of it is done during elaboration for making executable prototype of project.]

---
RUP Life Cycle in brief
RUP Life Cycle in brief
The dynamic structure deals with the Life Cycle or time dimension of a project
Shows cycles which contains 4 phases
  - Inception closed with Milestone : Life Cycle Objective
  - Elaboration closed with Milestone: Life Cycle Architecture
  - Construction closed with Milestone: Initial Operational Capability
  - Transition closed with Milestone : Product Release
Below table shows how project time and effort is divided between phases
Transition
Construction
Elaboration
Inception
10%
65%
20%
5%
Effort
10%
50%
30%
10%
Time
[Speaker Notes: Dynamic structure tells how project goes over time. it determine how should project be in some certain time , by using 4 phases, and iterations also. Each phase has its own purpose and will end with a predetermined milestone . In any phase if project does not reach the criteria we should reconsider the project or even abandon it. Project time and Effort is divided between phases ,its not a must be division rather it’s a best practice, so try to accept it in your own works.]

---
Inception phase
Inception phase
Inception is the first of four RUP phase its all about getting familiar with Project goal and Scope .this phase help you determine the project feasibility , what customer want and how will you get into more resource consumable phase.
Objective:
Understand what to build.
  - A vision document:
  - Optional business model
  - An initial project glossary
Identify key system functionality.
  - A initial use-case model (10% -20%) complete.
Determine at least one possible solution.
  - One or several prototypes.
Understand the costs, schedule, and risks associated with the project.
  - An initial risk assessment.
  - Business case
Decide what process to follow and what tools to use.
  - A project plan
[Speaker Notes: The overriding goal of the inception phase is to achieve concurrence among all stakeholders on the Life Cycle objectives for the project.  The inception phase is of significance primarily for new development efforts, in which there are significant business and requirements risks which must be addressed before the project can proceed. For projects focused on enhancements to an existing system, the inception phase is more brief, but is still focused on ensuring that the project is both worth doing and possible to do. Inception is the first of the four Life Cycle phases in the RUP. It is really all about understanding the project scope and objectives and getting enough information to confirm that you should proceed or perhaps convince you that you shouldn't. The five basic objectives of the Inception phase are Understand what to build Determine the vision, the scope of the system, and its boundaries, that is, what is inside the system and what is outside. Identify who wants this system and what it is worth to them. Identify key system functionality Decide which use cases (which ways of using the system) are most critical. Determine at least one possible solution Identify at least one candidate architecture. Understand the costs, schedule, and risks associated with the project. Understand the costs, schedule, and risks associated with the project: It’s important to know what to build but also you should determine how it will be build from Cost and time view. Most of project cost is because resources which you decide to use, for handling this element its better to have a business study or business case for project. Decide what process to follow and what tools to use : its important to understand what we should use in building project , which framework , development tools , what is environment,…]

---
Life Cycle Objectives Milestone
Life Cycle Objectives Milestone
Its first project Milestone which help to abort project or reconsider it early
And let us not to focus on a doomed to fail project.
Milestone:
  - cost/schedule estimates.
  - Requirements understanding.
  - Credibility of the cost/schedule estimates, priorities, risks, and development process.
  - Depth and breadth of any architectural prototype.
  - Actual expenditures versus planned expenditures.
First Major
Milestone
Transition
Construction
Inception
Elaboration
time
[Speaker Notes: At the end of the Inception phase is the first major project milestone, called Life Cycle Objective Milestone. At this point, you examine the Life Cycle objectives of the project. The project should be aborted or reconsidered if it fails to reach this milestone. If your project is doomed to fail, it is better to realize this early than late, and the iterative approach combined with this milestone may force such an early epiphany. This milestone answer some question which is always early question of projects Question like : How is cost and schedule , is it feasible with the cost / schedule that customer suggest at first? What is requirement from technical requirements to requirement which customer or other entities should provide. By providing the Team with a miles wide , two inch depth description of architecture it shoot-out some of risk in early. It tell you does the risk , time , priorities which you determine are correct and if not how much rework should be done to make them credible.]

---
Artifacts of Inception phase  In order of importance
Artifacts of Inception phase
In order of importance
Vision documents
Business Case
Risk List
Software Development Plan
Iteration Plan
Development Process
Development Infrastructure
Glossary
Use-Case Model (Actors, Use Cases)
Prototypes (Optional)
[Speaker Notes: Vision :The project's core requirements, key features, and main constraints are documented. Business Case :Defined and approved. Risk List :Initial project risks identified. Software Development Plan :Initial phases, their durations and objectives identified. Resource estimates (specifically the time, staff, and development environment costs in particular) in the Software Development Plan must be consistent with the Business Case. The resource estimate may encompass either the entire project through delivery, or only an estimate of resources needed to go through the elaboration phase. Estimates of the resources required for the entire project should be viewed as very rough, a "guesstimate" at this point. This estimate is updated in each phase and each iteration, and becomes more accurate with each iteration. Depending on the needs of the project, one or more of the enclosed "Plan" artifacts may be conditionally completed. In addition, the enclosed "Guidelines" artifacts are typically in at least a "draft" form. Iteration Plan : Iteration plan for first Elaboration iteration completed and reviewed. Development Process: Adaptations and extensions to the Rational Unified Process, documented and reviewed. This typically includes project specific guidelines and templates. Development Infrastructure :All tools to support the project are selected. The tools necessary for work in Inception are installed. In particular, the Configuration Management environment should be set up. Glossary :Important terms defined; glossary reviewed. Use-Case Model (Actors, Use Cases) : Important actors and use cases identified and flows of events outlined for only the most critical use cases Prototypes (Optional) :One or more proof of concept prototypes, to support the Vision and Business Case, and to address very specific risks.]

---
Elaboration phase
Elaboration phase
Objectives:
Deeper Requirement understanding
    - At least 80% complete use-case model
    - Supplementary requirements capturing
      - non functional requirements
      - None Use case requirement
Architect consideration.
    - A Software Architecture Description.
    - An executable architectural prototype.
Risk mitigation and Accurate Cost/Scapulae
    - A revised risk list and a revised business case.
Development Case refinement
    - A development plan for the overall project
      - coarse-grained project plan
        - showing iterations
        - evaluation criteria for each iteration.
Elaboration is the second of the four phases in the RUP approach. The goal of the Elaboration phase is to define and baseline the architecture of the system in order to provide a stable basis for the bulk of the design and implementation effort in the Construction phase. The architecture evolves out of a consideration of the most significant requirements (those that have a great impact on the architecture of the system) and an assessment of risks.
[Speaker Notes: The goal of the elaboration phase is to baseline the architecture of the system to provide a stable basis for the bulk of the design and implementation effort in the construction phase. The architecture evolves out of a consideration of the most significant requirements (those that have a great impact on the architecture of the system) and an assessment of risk. The stability of the architecture is evaluated through one or more architectural prototypes. The purpose of the elaboration phase is to analyze the problem domain, establish a sound architectural foundation, develop the project plan, and eliminate the highest risk elements of the project. To accomplish these objectives, you must have the “mile wide and inch deep” view of the system. Architectural decisions have to be made with an understanding of the whole system: its scope, major functionality and nonfunctional requirements such as performance requirements. It is easy to argue that the elaboration phase is the most critical of the four phases. At the end of this phase, the hard “engineering” is considered complete and the project undergoes its most important day of reckoning: the decision on whether or not to commit to the construction and transition phases. For most projects, this also corresponds to the transition from a mobile, light and nimble, low-risk operation to a high-cost, high-risk operation with substantial inertia. While the process must always accommodate changes, the elaboration phase activities ensure that the architecture, requirements and plans are stable enough, and the risks are sufficiently mitigated, so you can predictably determine the cost and schedule for the completion of the development. Conceptually, this level of fidelity would correspond to the level necessary for an organization to commit to a fixed-price construction phase.]

---
Milestone : Life Cycle Architecture
Milestone : Life Cycle Architecture
This milestone tell help to determine if project plane, vision , architecture
Are enough good to achieve project goals? If not Abort the project or
reconsider it very seriously
Is vision Stable?
Is architecture stable?
Does executable show true risk management?
Is next phase (Construction) plane is accurate?
Does current vision could be achieved?
Is the actual resource expenditure versus planned expenditure acceptable?
Major
Milestones
Transition
Construction
Inception
Elaboration
time
[Speaker Notes: At the end of the elaboration phase is the second important project milestone, the Life Cycle Architecture Milestone. At this point, you examine the detailed system objectives and scope, the choice of architecture, and the resolution of the major risks.]

---
Artifact of Elaboration phase In order of importance
Artifact of Elaboration phase
In order of importance
Prototypes
Risk List
Development Process
Development Infrastructure
Software Architecture Document
Design Model (and all constituent artifacts)
Data Model
Implementation Model
Software Development Plan
Iteration Plan
Use-Case Model (Actors, Use Cases)
Supplementary Specifications
Optional Artifacts
  - Business Case
  - Analysis Model
[Speaker Notes: Prototypes :One or more executable architectural prototypes have been created to explore critical functionality and architecturally significant scenarios. See the note below on the role of prototyping Risk List:Updated and reviewed. New risks are likely to be architectural in nature, primarily relating to the handling of non-functional requirements. Development Process :The development process, including any project-specific guidelines and templates, has been refined based on early project experience, and is sufficiently defined for the construction phase to proceed. Development Infrastructure :The development environment for construction is in place, including all tools and automation support for the process. Software Architecture Document :Created and base lined, including detailed descriptions for the architecturally significant use cases (use-case view), identification of key mechanisms and design elements (logical view), plus definition of the process view and the deployment view if the system is distributed or must deal with concurrency issues. Design Model :Defined and base lined. Design use-case realizations for architecturally significant scenarios have been defined and required behavior has been allocated to appropriate design elements. Components have been identified and the make/buy/reuse decisions sufficiently understood to determine the construction phase cost and schedule with confidence. The selected architectural components are integrated and assessed against the primary scenarios. Lessons learned from these activities may well result in a redesign of the architecture, taking into consideration alternative designs or reconsideration of the requirements. Data Model: Defined and base lined. Major data model elements (e.g. important entities, relationships, tables) defined and reviewed. Implementation Model Vision :Initial structure created and major components prototyped. Vision : Refined, based on new information obtained during the phase, establishing a solid understanding of the most critical use cases that drive the architectural and planning decisions. Software Development :Updated and expanded to cover the Construction and Transition phases. Iteration plan: Iteration plan for the construction phase completed and reviewed. Use-Case Model : A use-case model (approximately 80% complete)-all use cases having been identified in the use-case model survey, all actors having been identified, and most use-case descriptions (requirements capture) have been developed. Supplementary Specifications: Supplementary requirements capturing the non functional requirements are documented and Business Case : Updated if architectural investigations uncover issues that change fundamental project assumptions. Analysis Model:May be developed as a formal artifact; frequently not formally maintained, evolving into an early version of the Design Model instead.]

---
Construction Phase
Construction Phase
Construction is really about cost-efficient development of a complete product—an operational version of your system—that can be deployed in the user community
Objectives:
Minimize development costs and achieve some degree of parallelism
Iteratively develop a complete product that is ready to transition to its user community
The software product integrated on the adequate platforms.
The user manuals.
A description of the current release.
[Speaker Notes: During the construction phase, all remaining components and application features are developed and integrated into the product, and all features are thoroughly tested. The construction phase is, in one sense, a manufacturing process where emphasis is placed on managing resources and controlling operations to optimize costs, schedules, and quality. In this sense, the management mindset undergoes a transition from the development of intellectual property during inception and elaboration, to the development of deployable products during construction and transition. Many projects are large enough that parallel construction increments can be spawned. These parallel activities can significantly accelerate the availability of deployable releases; they can also increase the complexity of resource management and workflow synchronization. A robust architecture and an understandable plan are highly correlated. In other words, one of the critical qualities of the architecture is its ease of construction. This is one reason why the balanced development of the architecture and the plan is stressed during the elaboration phase. The outcome of the construction phase is a product ready to put in hands of its end-users.]

---
Milestone : Initial Operational Capability
Milestone : Initial Operational Capability
The Construction phase ends with an important project milestone,
 the Initial Operational Capability Milestone, which is used to determine
 whether the product is ready to be deployed into a beta test environment
by answering (among others) the following questions
Is this product release stable and mature enough to be deployed in the user community?
Are all the stakeholders ready for the transition into the user community?
Are actual resource expenditures versus planned expenditures still acceptable?
Major
Milestones
Transition
Construction
Inception
Elaboration
time
[Speaker Notes: At the end of the construction phase is the third major project milestone (Initial Operational Capability Milestone). At this point, you decide if the software, the sites, and the users are ready to go operational, without exposing the project to high risks. This release is often called a “beta” release.]

---
Artifacts of Construction phase In order of importance
Artifacts of Construction phase
In order of importance
"The System“
Implementation Model
Iteration Plan
Design Model
Development Process
Development Infrastructure
Data Model
Optional Artifacts
  - Supplementary Specifications
  - Use-Case Model (Actors, Use Cases)
[Speaker Notes: "The System“ : The executable system itself, ready to begin "beta" testing. Implementation Model :Expanded from that created during the elaboration phase; all implementation elements created by the end of the construction phase. Iteration Plan: Iteration plan for the transition phase completed and reviewed. Design Model :Updated with new design elements identified during the completion of all requirements. Development Process: The development process, including the development case and any project-specific guidelines and templates, has been refined based on project experience, and is sufficiently defined for the next phase to proceed. Development Infrastructure :The development environment for transition is in place, including all tools and automation support for the process. Data Model: Updated with all elements needed to support the persistence implementation (e.g. tables, indexes, object-to-relational mappings, etc.) Supplementary Specifications: Updated with new requirements (if any) discovered during the construction phase. Use-Case Model : Updated with new use cases (if any) discovered during the construction phase.]

---
Transition Phase
Transition Phase
The purpose of the transition phase is to transition the software product to the user community. Once the product has been given to the end user, issues usually arise that require you to develop new releases, correct some problems, or finish the features that were postponed.
Objectives:
“beta testing” to validate the new system against user expectations
parallel operation with a legacy system that it is replacing
conversion of operational databases
training of users and maintainers
roll-out the product to the marketing, distribution, and sales teams
Improve future project performance through lessons learned
[Speaker Notes: The focus of the Transition Phase is to ensure that software is available for its end users. The Transition Phase can span several iterations, and includes testing the product in preparation for release, and making minor adjustments based on user feedback. At this point in the Life Cycle, user feedback should focus mainly on fine tuning the product, configuring, installing and usability issues, all the major structural issues should have been worked out much earlier in the project Life Cycle. The purpose of the transition phase is to transition the software product to the user community. Once the product has been given to the end user, issues usually arise that require you to develop new releases, correct some problems, or finish the features that were postponed. The transition phase is entered when a baseline is mature enough to be deployed in the end-user domain. This typically requires that some usable subset of the system has been completed to an acceptable level of quality and that user documentation is available so that the transition to the user will provide positive results for all parties. The transition phase focuses on the activities required to place the software into the hands of the users. Typically, this phase includes several iterations, including beta releases, general availability releases, as well as bug-fix and enhancement releases. Considerable effort is expended in developing user-oriented documentation, training users, supporting users in their initial product use, and reacting to user feedback. At this point in the Life Cycle, however, user feedback should be confined primarily to product tuning, configuring, installation, and usability issues.]

---
Milestone: Product Release
Milestone: Product Release
Transition ends with the fourth major project milestone, the Product Release Milestone, to determine whether the objectives were met and if you should start another development cycle. (Several development cycles may have been already planned during Inception.) In some cases this milestone may coincide with the end of the Inception phase for the next cycle
Is the user satisfied?
Are the actual resources expenditures versus planned expenditures still acceptable?
Major
Milestones
Transition
Construction
Inception
Elaboration
time
[Speaker Notes: At the end of the transition phase is the fourth important project milestone, the Product Release Milestone. At this point, you decide if the objectives were met, and if you should start another development cycle. In some cases, this milestone may coincide with the end of the inception phase for the next cycle.]

---
Artifacts of Transition phase  In order of importance
Artifacts of Transition phase
In order of importance
Implementation Elements
    - The implementation is complete and base lined, and the deployable elements have been incorporated in the final product
Shrink-wrap Product Packaging (Optional )
    - In the case of creating a shrink-wrap product, the contractor will need the necessary packaging artifacts to help retail the product.

---
Dynamic Elements Phases and Milestones , a Review
Dynamic Elements Phases and Milestones , a Review
time
Inception
Define scope of project
Life Cycle Objectives
…
Elaboration
Plan project, specify features, baseline architecture
Life Cycle Architecture
…
Initial Operational Capability
Construction
Build product
…
Major Milestones
Transition
Transition product to end user community
…
Product Release

---
System Evolution
System Evolution
RUP is So flexible , you finish the project and deliver it’s final operational version.
But after a while you or your customer find some new requirement that will be better to add to project in this condition evolution cycles start .
In each evolution you made some new feature or enhance some already available feature and announce a new version. its the evolutionary aspect or software generation
  - Four phases form one development cycle and produce a generation of the system
  - Significant user enhancement, business or mission changes, or technology changes trigger a new generation
  - the inception and elaboration phases would be considerably smaller
V1
Initial Project
Cycle
V2
Evolution
Cycles
V3
I E C T
I E C T
I E C T
[Speaker Notes: The four phases (I, E, C, and T) constitute a development cycle and produce a software generation. A software product is created in an initial development cycle. Unless the life of the product stops at this point, a product will evolve into its next generation by a repetition of the sequence of inception, elaboration, construction, and transition phases, but with different emphases on the various phases. We call these periods evolution cycles As the product goes through several evolution cycles, new generations of the product are produced. Evolution cycles can be triggered by user-suggested enhancements, changes in the user's context, changes in the underlying technology, or reaction to the competition. In practice, cycles may overlap slightly: the inception and elaboration phase may begin during the final part of the transition phase of the previous cycle.]

---
EUP (RUP evolution)
EUP (RUP evolution)
Additional phases
Production Phase
    - Ensure that the system is available to end users.
    - Modify the system to address minor defects.
    - Support users in using the system.
    - Manage defect reports and enhancement requests.
Retirement Phase
    - Complete the removal of the system.
    - Ensure minimal interruption to users.
    - Ensure minimal impact to business operations.

---
References
References
The Rational Unified Process An Introduction, Second Edition Philippe Kruchten , Publisher: Addison Wesley
Rational Unified Process Best Practices for Software Development Teams Rational Software White Paper TP026B, Rev 11/01
MSF Process Model v. 3.1 , Microsoft June 2002
Software Development for Small Teams: A RUP-Centric Approach By Gary Pollice, Liz Augustine, Chris Lowe, Jas Madhur .Publisher : Addison Wesley
The Rational Unified Process Made Easy: A Practitioner's Guide to the RUP, By Per Kroll, Philippe Kruchten. Publisher : Addison Wesley
The Rational Unified Process An Introduction, Second Edition Philippe Kruchten. Publisher: Addison Wesley
From Waterfall to Iterative Life Cycle – A tough transition for project managers
P. Krutchen, Architectural Blueprints - The "4+1" View Model of Software
Architecture, www.rational.com
RUP 2005 product documentation.
Extreme methodology

---
Thank you
Thank you
Thank you for your attentions.
All your suggestion and comment are welcome.
You can contact me via :
kalali@gmail.com
Masoud Kalali
http://weblogs.java.net/blog/kalali/
March 2005